## Week 1
Monday
Start | Finish | Type | Total Time (hr)
15:30 | 16:30 | Setup | 1
18:15 | 19:00 | Setup | 0.75
22:00 | 23:30 | Setup | 1.5
3.25
Tuesday
Start | Finish | Type | Total Time (hr)
8:15 | 9:00 | Emotiv Research | 0.75
13:00 | 13:45 | Emotiv Research | 0.75
13:45 | 15:00 | Connecting to Emotiv Headset | 1.25
19:45 | 23:15 | Creating Wrapper Classes for Emotiv API | 3.5
Today's Total |  |  | 6.25
Wednesday
Start | Finish | Type | Total Time (hr)
12:00 | 14:30 | Coding with/Studying Emotiv API | 2.5
14:30 | 15:00 | Emotiv Research | 0.5
Today's Total |  |  | 3
Thursday
Start | Finish | Type | Total Time (hr)
13:00 | 15:00 | Coding - Recognizing Dongle Insertion | 2
18:00 | 0:00 | Coding - Wire up for Create/Load Profiles | 6
Today's Total |  |  | 8
Friday
Start | Finish | Type | Total Time (hr)
10:00 | 11:00 | Research - Learned XNA is preferable over WPF | 1
13:00 | 15:00 | Tutorial Coding with XNA | 2
Today's Total |  |  | 3
Saturday
Start | Finish | Type | Total Time (hr)
Sunday
Start | Finish | Type | Total Time (hr)
This Week's Total Hours |  |  | 23.5

## Week 2
Monday
Start | Finish | Type | Total Time (hr)
Tuesday
Start | Finish | Type | Total Time (hr)
Wednesday
Start | Finish | Type | Total Time (hr)
Thursday
Start | Finish | Type | Total Time (hr)
Friday
Start | Finish | Type | Total Time (hr)
Saturday
Start | Finish | Type | Total Time (hr)
Sunday
Start | Finish | Type | Total Time (hr)

## Week 3
Monday
Start | Finish | Type | Total Time (hr)
12:30 | 14:30 |  | 2
19:00 | 21:00 | Research For UI Controls | 2
Today's Total |  |  | 4
Tuesday
Start | Finish | Type | Total Time (hr)
12:30 | 15:00 | Installing UI Controls | 2.5
21:00 | 0:00 | Installing UI Controls | 3
Today's Total |  |  | 5.5
Wednesday
Start | Finish | Type | Total Time (hr)
12:30 | 15:00 | Create/Load Profiles | 2.5
18:00 | 21:00 | Create/Load Profiles | 3
22:00 | 1:30 | Create/Load Profiles(Completed) | 3.5
1:30 | 2:00 | Project Management/Source Control | 0.5
Today's Total |  |  | 9.5
Thursday
Start | Finish | Type | Total Time (hr)
12:00 | 15:00 | Create Main Menu flow | 3
18:00 | 20:00 | Create Main Menu flow | 2
Today's Total |  |  | 5
Friday
Start | Finish | Type | Total Time (hr)
Saturday
Start | Finish | Type | Total Time (hr)
14:00 | 16:00 | Setup the settings menu | 2
Today's Total |  |  | 2
Sunday
Start | Finish | Type | Total Time (hr)
Week 3 Total |  |  | 26

## Week 4
Monday
Start | Finish | Type | Total Time (hr)
9:00 | 11:00 | Implementing Settings Menu | 2
12:30 | 15:00 | Implementing Settings Menu | 2.5
Today's Total |  |  | 4.5
Tuesday
Start | Finish | Type | Total Time (hr)
12:00 | 15:00 | Implementing Settings Menu | 3
20:00 | 22:00 | Implementing Settings Menu | 2
22:00 | 6:00 | Training/Saving/Reading Cognitiv Actions | 8
Today's Total |  |  | 13
Wednesday
Start | Finish | Type | Total Time (hr)
11:00 | 12:00 | Training/Saving/Reading Cognitiv Actions | 1
12:30 | 15:00 | Creating Contact Quality Panel | 2.5
Today's Total |  |  | 3.5
Thursday
Start | Finish | Type | Total Time (hr)
9:00 | 11:00 | Creating Contact Quality Panel | 2
14:00 | 15:00 | Creating Contact Quality Images | 1
20:00 | 22:00 | Creating Contact Quality Images | 2
0:00 | 1:00 | Project Management/Source Control/Time Log | 1
1:00 | 1:40 | Positioning Contact Quality Images | 0.66
1:40 | 4:00 | Updating Contact Quality Images | 2.33
Today's Total |  |  | 9
Friday
Start | Finish | Type | Total Time (hr)
12:00 | 15:00 | Pause Functionality for EEG abnormalities | 3
Today's Total |  |  | 3
Saturday
Start | Finish | Type | Total Time (hr)
12:00 | 2:00 | Pause Functionality for EEG abnormalities | 2
Sunday
Start | Finish | Type | Total Time (hr)

## Week 5
Monday
Start | Finish | Type | Total Time (hr)
12:30 | 15:00 | Research On USB Relay | 2.5
17:00 | 18:00 | Research On USB Relay | 1
Today's Total |  |  | 3.5
Tuesday
Start | Finish | Type | Total Time (hr)
12:30 | 15:00 | Creating 3D World | 2.5
Today's Total |  |  | 2.5
Wednesday
Start | Finish | Type | Total Time (hr)
Thursday
Start | Finish | Type | Total Time (hr)
12:30 | 15:00 | Creating 3D World | 2.5
Today's Total |  |  | 2.5
Friday
Start | Finish | Type | Total Time (hr)
Saturday
Start | Finish | Type | Total Time (hr)
14:00 | 17:00 | Creating 3D World | 3
Today's Total |  |  | 3
Sunday
Start | Finish | Type | Total Time (hr)

## Week 6
Monday
Start | Finish | Type | Total Time (hr)
13:00 | 15:00 | Creating the 3D World | 2
Today's Total |  |  | 2
Tuesday
Start | Finish | Type | Total Time (hr)
9:30 | 12:00 | Creating the 3D World | 2.5
13:00 | 15:00 | Creating the 3D World | 2
Today's Total |  |  | 4.5
Wednesday
Start | Finish | Type | Total Time (hr)
9:30 | 12:30 | Creating the 3D World | 3
13:00 | 15:00 | Creating the 3D World | 2
Today's Total |  |  | 5
Thursday
Start | Finish | Type | Total Time (hr)
9:30 | 12:30 | Creating the 3D World | 3
13:00 | 15:00 | Creating the 3D World | 2
Today's Total |  |  | 5
Friday
Start | Finish | Type | Total Time (hr)
9:30 | 12:30 | Creating the 3D World | 3
13:00 | 15:00 | Creating the 3D World | 2
Today's Total |  |  | 5
Saturday
Start | Finish | Type | Total Time (hr)
Sunday
Start | Finish | Type | Total Time (hr)
Week Total |  |  | 21.5

## Week 7
Monday
Start | Finish | Type | Total Time (hr)
9:30 | 12:30 | Implementing the 3D World | 3
13:00 | 15:00 | Implementing the 3D World | 2
18:00 | 20:00 | Implementing the 3D World | 2
Today's Total |  |  | 7
Tuesday
Start | Finish | Type | Total Time (hr)
9:30 | 12:30 | Moving the Virtual Car | 3
13:00 | 15:00 | Moving the Virtual Car | 2
22:30 | 23:00 | Research on USB Relay API | 0.5
23:00 | 1:30 | Creating USB Relay Interface | 2.5
Today's Total |  |  | 8
Wednesday
Start | Finish | Type | Total Time (hr)
9:30 | 12:30 | Creating USB Relay Interface | 3
13:00 | 15:00 | Creating USB Relay Interface | 2
Today's Total |  |  | 5
Thursday
Start | Finish | Type | Total Time (hr)
13:00 | 15:00 | Restricting Active Trained Actions | 2
Today's Total |  |  | 2
Friday
Start | Finish | Type | Total Time (hr)
10:30 | 12:30 | Creating RC Car Component | 2
13:00 | 15:00 | Creating RC Car Component | 2
Today's Total |  |  | 4
Saturday
Start | Finish | Type | Total Time (hr)
Sunday
Start | Finish | Type | Total Time (hr)
5:00 | 8:30 | Wiring RC Car to Computer | 3.5
Week Total |  |  | 29.5

## Week 8
Monday
Start | Finish | Type | Total Time (hr)
Tuesday
Start | Finish | Type | Total Time (hr)
17:00 | 18:00 | Fixing 3D World | 1
Today's Total |  |  | 1
Wednesday
Start | Finish | Type | Total Time (hr)
13:30 | 15:00 | Fixing 3D World | 1.5
17:00 | 19:00 | Fixing 3D World | 2
Today's Total |  |  | 3.5
Thursday
Start | Finish | Type | Total Time (hr)
Friday
Start | Finish | Type | Total Time (hr)
Saturday
Start | Finish | Type | Total Time (hr)
Sunday
Start | Finish | Type | Total Time (hr)

## Week 9
Monday
Start | Finish | Type | Total Time (hr)
Tuesday
Start | Finish | Type | Total Time (hr)
Wednesday
Start | Finish | Type | Total Time (hr)
Thursday
Start | Finish | Type | Total Time (hr)
Friday
Start | Finish | Type | Total Time (hr)
Saturday
Start | Finish | Type | Total Time (hr)
Sunday
Start | Finish | Type | Total Time (hr)